## Slide 1: Michael J. Gavin CPA/ABV PLLC
February 25th, 2013
MMC
Phase II
Kick Off
Meeting

## Slide 2: Kick Off Agenda
Meeting Goals
  Review Phase II Scope
  Review Team Members
  Review Approach
  Review Schedule

## Slide 3: Phase II Scope
  Finish Contract Analysis (Commission, Non Commission (Fixed Price) & Risk)
    Contract Opportunity vs. Actual Opportunity
    Hi-light Variance
  Compare and Rank Contracts
    Revenue Effectiveness
    Risk
    Lost Opportunities
  Summarize Contracts
    Actions, Recommendations & Expirations

## Slide 4: Phase II Scope (Continued)
  Finish Proposal Analysis
    Review most recent proposals processed
    Review the proposals that tie to the key contracts analyzed (if available)
  Provide Proposal Recommendations
    Future documents and procedures to be used

## Slide 5: Phase II Scope (Continued)
  Analyze Expense & Capital Budget Process
    Observe and Obtain documentation
    Assist in Budgeting Process
    Assist in documenting “to be” process
  Provide recommendations in MMC’s long term Strategic Direction
    Revenue, Expense and Capital Growth
    Organizational Growth
    Assist in establishing a Strategic Plan

## Slide 6: Approach & Schedule
Axiom to provide approx.. 1 day a week (8 hrs. max) worth of effort
  Combination of Carl & Mike
  Work to be done remotely from Axiom office
  Onsite when necessary and as approved by MMC
Carl and Mike to interface through Eric at MMC
Progress reviews to be held every 4 to 6 weeks with Dan

## Slide 7: Team Members
Axiom
  Mike
  Carl
MMC
  Aric
  Andonella
  Scott
  Dan
  Others (when as needed by MMC, i.e.. Carmen)

## Slide 8: Michael J. Gavin CPA/ABV PLLC
September 12th, 2012
MMC
Phase II
Work

## Slide 9
Dan,
Thanks for talking with us on Thursday. Included within the presentation are the items we reviewed with you last week:
Phase II Scope
Info needed to be gathered by MMC
Axiom Deliverables
Milestones (who’s due dates will be determined based on MMC’s availability)
As discussed, the cost range for this phase is $6,500 to $7,500. We look forward to working with you and your team on this next phase.
Regards,
Mike
9

## Slide 10: Phase II Scope
Gather Contract Data for workshop MMC
Analyze Data for workshop Axiom
Create sample forms & metrics for workshop Axiom
½ Day Workshop reviewing the sample contracts Both
  Results
  Forms
  Metrics
Participate in Monthly Follow on review Axiom

## Slide 11: Information to be gathered by MMC:
11
Selection of 3 contracts by Dan from each of the main categories -Commission, Non-commission and Risk
Copy of the original contract and any updates, addendums etc.
Financial analysis prior to the engagement of the contract or any subsequent analysis after execution of it
Current metrics that are used to track the contract—both client agreed upon and internal by MMC
Efficiencies of the contract—“is there money left on the table?”, Have maximum revenues been recognized by the contract?
Organizational support for the contract—reporting scheme from those on the day to day up through management to the CEO

## Slide 12: Items to be delivered by Axiom:
12
Financial Analysis of the 3 (MMC) selected contracts
Methods, Templates and Cost Model to be used by MMC for follow on analysis of:
  Balance of (existing) contracts
  Future contracts / amendments
Metrics to be used for follow on performance tracking of MMC contracts

## Slide 13: Milestones
13
Data Gathering __/__/__ (by MMC)
Data Analysis __/__/__ (by Axiom)
Workshop __/__/__ (Both)
Initial Monthly Metrics __/__/__ (via MMC invite) Review participation
(Dates to be determined based on MMC’s availability)